## Slide 1: NRT Data Pipeline
Milestones
One-Line Summary for Executive Dashboard | 
Automated NRT pipeline for incremental data loads established with S3 events, Lambda validation, and Glue orchestration; progressing towards advanced validation, merging, and end-to-end testing. | 
Out of Scope | 
Executive Summary | 
The Near Real-Time (NRT) Data Pipeline initiative is progressing according to plan, focusing on building a scalable, event-driven architecture to support incremental data ingestion and processing. Leveraging AWS S3 event notifications, Lambda, and Glue, the pipeline automates the validation, transformation, and loading of incoming data files with robust audit, traceability, and exception handling. | 
Key Accomplishments from Last Update | Key Upcoming Activities
S3 event notification setup complete Lambda validation function developed and integrated Config table created in Postgres audit End-to-end trigger from S3 to Glue job validated | Develop config files for each source file Enhance Glue for file and data validation Implement Glue logic for merging into curated and published tables Conduct end-to-end pipeline testing
Team Members | Status
Lokesh | 
Issue / Risk | Action / Resolution | Dependent Work Streams | Owner
Topics | Target Date
S3 Event & Lambda Setup | 22nd Sep 2025
Glue Validation Logic | 25th Sep 2025
End to End Testing | 26th Sep 2025
Off Track
Complete
(S) New scheduled date
At Risk
On Track
Not Started
24/09/2025
Capabilities | Status
Automated file trigger and validation initiation | ü
File/data validation and transformation workflow | ⏳
Full pipeline validation and quality assurance | ○
Notes: Team: Lokesh (Developer)